## Instructions
Initia Risk - Example action register
What this template is
A starter action register you can lift and edit. Each row is a real piece of work linked to a risk. This is an example register, not a system upload file.
How to use it
Step | What to do | Why it matters
1 | Keep Action name short and recognisable. | The name is what appears in board and committee packs.
2 | Give every open action a named owner and a due date. | An action without both is a wish, not a control response.
3 | Link the action to a risk where one exists. | Unlinked actions are harder to prioritise and easier to forget.
4 | Use Completed or Cancelled for historic work. | Closed items keep their original dates. Do not reopen them to tidy the list.
5 | Replace the examples with your own, or add from the first empty row. | The example set is illustrative, not a recommended programme of work.

## Reference
Reference values - edit to match your firm
These lists drive the dropdowns on the Action register sheet.
Action owners | Statuses | Priorities | Linked record types
Alex Mercer | Planned | Low | Standalone
Priya Shah | In Progress | Medium | Risk
James Cole | Overdue | High | Control
Hannah Reid | Completed
Chris Adeyemi | Cancelled
Laura Bennett
Omar Farouk
Rachel Ng

## Action register
Initia Risk - Example action register
Action name | Description | Owner | Status | Priority | Raised | Due date | Closed date | Closure notes | Linked risk | Commentary
Clear unreconciled cash items older than 30 days | Bring the bank rec exception log to zero items older than 30 days and agree a standing clearance SLA with Finance. | Alex Mercer | In Progress | High | 2026-04-02 | 2026-07-31 |  |  | Failure of bank reconciliations | Three items remain from March. Owner has weekly checkpoint with Financial Controller.
Stand up maker-checker on regulatory returns | Document the reviewer role, the source-data checklist, and the sign-off evidence to be retained. | Priya Shah | Planned | High | 2026-05-12 | 2026-08-29 |  |  | Inaccurate regulatory returns | Depends on the Finance operating calendar being locked for H2.
Appoint deputies for material process owners | Name a deputy for each material process and complete a documented walkthrough. | James Cole | In Progress | Medium | 2026-03-18 | 2026-09-30 |  |  | Key person dependency | Cover is in place for Operations. Finance and Compliance still open.
Test exit plan for the material outsourcing arrangement | Run a tabletop of the contracted exit and insource path for the primary operations BPO. | Hannah Reid | Planned | High | 2026-06-01 | 2026-10-31 |  |  | Outsourced service failure | Legal to confirm the notice period before the exercise is scheduled.
Complete Q2 privileged access review | Review all privileged accounts, revoke unjustified access, and file the sign-off pack. | Chris Adeyemi | Completed | High | 2026-04-01 | 2026-06-30 | 2026-06-24 | Review complete. Four accounts revoked. Pack filed in the control evidence folder. | Ransomware disrupting operations | Next review due end of Q3.
Close overdue SMCR record gaps | Bring certified-person records up to date and confirm the notification log is complete. | Omar Farouk | Overdue | High | 2026-02-10 | 2026-05-30 |  |  | Late regulatory notification | Two certified persons still missing a current statement of responsibilities.
Table ransomware recovery scenario at ExCo | Present recovery time, communication plan, and residual position after the latest backup test. | Chris Adeyemi | Planned | Medium | 2026-06-15 | 2026-09-15 |  |  | Ransomware disrupting operations | Waiting on the Q3 backup restore test result.
Retire the legacy onboarding journey | Remove the journey that failed fair-value assessment and migrate remaining customers. | Laura Bennett | In Progress | High | 2026-01-20 | 2026-11-28 |  |  | Unfair customer outcomes | Migration 40% complete. Complaints MI being watched weekly.
Note on B3: Short name as it should appear in a committee pack.
Note on C3: What will be true when this is done, not a task list.
Note on D3: Named person, not a team.
Note on E3: Planned, In Progress, Overdue, Completed, or Cancelled.
Note on F3: Low / Medium / High relative to residual exposure.
Note on J3: Required when status is Completed.
Note on K3: Must match a name on the Available risks sheet.

## Available risks
Available risks
Use a name from this list when linking an action to a risk.
Name | Type | Owner
Failure of bank reconciliations | Financial | Alex Mercer
Inaccurate regulatory returns | Financial | Priya Shah
Key person dependency | Operational | James Cole
Outsourced service failure | Operational | Hannah Reid
Ransomware disrupting operations | Technology | Chris Adeyemi
Unfair customer outcomes | Conduct | Laura Bennett
Late regulatory notification | Compliance | Omar Farouk
Failure to execute the growth plan | Strategic | Rachel Ng