## How to use
Spreadsheet-to-platform migration pack
A phased plan, an honest view of what actually breaks (people, not data), and a realistic parallel-run timeline. Built for a mid-market move off shared Excel, not a multi-year transformation programme.
What is in this workbook
Sheet | What it is for
What actually breaks | The failure modes that kill migrations.
Phased plan | Four phases with owners and exit criteria.
Timeline | A 16-week parallel-run plan you can edit.
How to use it
Step | What to do
1. | Do not start with data. Start with the methodology decisions and a cleaned register. Migrating a bad spreadsheet produces a bad platform faster.
2. | Name a first-line owner for the pilot area. If second line pilots on their behalf, you have learned nothing.
3. | Run the parallel period against a real committee date. If the pack cannot come from the platform that cycle, the parallel run was theatre.

## What actually breaks
What actually breaks
Failure | What it looks like | What to do instead
The taxonomy fight | Two teams discover they have been using 'Operational' to mean different things. | Lock the methodology pack before import. Do not import competing type lists.
Owners who were never asked | Spreadsheet 'owners' were a column of names who have not seen the file in a year. | Confirm every owner in a 15-minute call. An unconfirmed owner is unassigned.
Residual scores that were typed | People want the platform to store the number they had in Excel. | Explain, once, that residual is calculated. If that is unacceptable, you are not ready to migrate.
The shadow file | A 'temporary' spreadsheet continues because the first pack from the system felt unfamiliar. | Agree in writing the date the shadow file is deleted. Put it in the project plan.
Evidence left in inboxes | Controls migrate. The proof of operation does not. | Pick a storage convention before phase 2. Do not invent it per team.
Training as a slide deck | A webinar is not adoption. People revert to emailing the coordinator. | Train on their risks, in their committee cycle, with their logins, or do not call it training.

## Phased plan
Phased plan
Phase | When | What happens | Owner | Exit criterion
0. Decide | Week 0-2 | Four methodology decisions signed off. Taxonomy agreed. Pilot area named. | Head of Risk | A two-page decision record.
1. Clean | Week 2-5 | Pilot register, controls and open actions cleaned. Owners confirmed. Duplicates killed. | Second line + pilot owner | A register you would be willing to show a NED.
2. Load | Week 5-8 | Pilot data in the platform. Users can log in. One assessment cycle run on the pilot set. | Vendor + Head of Risk | Pilot owners have updated at least one record themselves.
3. Parallel | Week 8-14 | One full committee pack from the platform, with the spreadsheet as back-up only. | Head of Risk | Committee receives the system pack. Shadow file marked for deletion.
4. Roll out | Week 14-16+ | Remaining areas loaded in waves. Shadow file deleted. BAU cadence on. | First-line directors | No parallel spreadsheet. Issues logged as BAU, not as 'the project'.

## Timeline
16-week timeline
Each column is two weeks.
Workstream | W1-2 | W3-4 | W5-6 | W7-8 | W9-10 | W11-12 | W13-14 | W15-16 | Notes
Methodology lock | [8 empty] | Four decisions + taxonomy.
Clean pilot register | [8 empty] | Owners confirmed.
Platform configuration | [8 empty] | Users, workflow, reporting.
Pilot load and training | [8 empty] | On their data.
Pilot assessment cycle | [8 empty] | First-line actually scores.
Committee pack from system | [8 empty] | Acceptance test.
Shadow file retired | [8 empty] | Delete, do not archive in AOB.
Wave 2 areas | [8 empty] | Only after the pack has landed.
Amber blocks are when that workstream is live. Move them, but do not overlap 'pack from system' with 'still cleaning the register'.